## Sheet1
Key Stages | Tasks | To be done by… | 2018 | [9 empty] | 2019
|  |  | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | KEY:
Building the Evidence Base | Compile report on consultation so far, key issues raised, SWOT analysis, assessment of strategic policy context, and any further evidence base/targeted consultation required | Completed | [23 empty] | Stage 1 JL support package completed
| Project plan completed | Completed
| Gather any additional information required following Stage 1 report | Largely completed | [23 empty] | Stage 2 JL support package (ongoing)
| Apply for Locality Technical Support for Housing Needs Assessment and Sites Options Assessment | SG/JL | [23 empty] | Statutory stages | bar: 2018 A
Further evidence: Non-designated heritage assets (part-done), Historic Core, Local Green Spaces, Community Facilities Audit, Housing Needs Assessment (affordable housing - CAN?) | bar: 2018 A
Undertake mapping exericise - e.g. Local Green Space, Heritage Assets (designated/non-designated/historic core for Lowick), Community Facilities Audit, Settlement Boundary, Housing Sites/Employment sites etc. | bar: 2018 M to 2018 M
Steering Group Meeting (9/5/18)
| Hold consultation event on proposed settlement boundary, and options for housing sites following Sites Options Assessment | SG/JL | bar: 2018 J
Consider applying for Design package if specific housing sites are proposed that should reflect specific design issues | bar: 2018 J
SG/JL | bar: 2018 J to 2018 A
| Draft planning policies and finalise site allocations etc. | SG/JL | bar: 2018 J to 2018 A
| Request that NCC considers whether the policies and proposals you have developed warrant a formal Strategic Environmental Assessment and Habitats Regulations Assessment (3 weeks) | SG/JL | bar: 2018 A to 2018 S
| If SEA is required, build in time for SEA and Habs Regs Assessment now (6 weeks minimum) | SG
| Request a list of 'strategic policies' from NCC, and check conformity with that Strategic Policy (Berwick upon Tweed Local Plan) | SG/NCC | bar: 2018 A
| Amend following SEA (if required) | SG/JL | bar: 2018 N to 2018 D
| Compile draft Neighbourhood Plan | SG/JL | bar: 2018 N to 2018 D
| Finalise evidence base information | SG/JL | bar: 2018 M to 2018 D
| Compile list of statutory consultees and local representative organisations (engagement strategy could inform this) - re-visit regularly | SG/JL/NCC | bar: 2018 O
Pre-Submission Consultation (Regulation 14) | Lowick Parish Council to consult on pre-submission draft Neighbourhood Plan and (if required) Environmental Report [Regulation 14] for 6 weeks | SG/JL
Final amendments to Plan before Submission | Consider commissioning a Health Check on the Plan | SG
| Make necessary amendments to Plan | SG/JL
| Write Basic Conditions Statement and Consultation Statement for submission to NCC | SG/JL
Submission Stage (Regulation 15) | Submit the Lowick Neighbourhood Plan to NCC as defined in Regulation 15. | SG
Publicising a plan (Regulation 16) | NCC Consultation on Plan (6 weeks)
Appoint Examiner (Regulation 17) | NCC will appoint an independent examiner with approval of Acomb Parish Council and send them the relevant documents | NCC/SG
Publication of examiner's report and modification if necessary (Regulations 18 and 19) | Modify or not? (NCC may make modifications to the Neighbourhood Plan before the referendum to ensure that it complies with the recommendations of the examiner's report) | NCC/SG
| Referendum | NCC/SG
| THE PLAN IS MADE | NCC