# Neighbourhood Plan – From Meeting 9th May 2018

| - Updated planner [JH] |  |
| --- | --- |
| - Application to Groundworks for further support, including Technical Support where appropriate [JH] |  |
| - Agreed settlement boundary to be drawn [JH] - Methodology Sketched - Submitted to JL for comments - Official Draft required? - Printed for Consultation |  |
| - Agreed Settlement Green Spaces to be mapped. [JH] - Notes on Green Spaces - Submitted to JL for comments - Official Draft for Consultation |  |
| - Housing sites map within the settlement boundary - Issues of development outwith boundary discussed - Meeting with CAN arranged for next time - Contact all landowners with proposals for comments [BARBER, BELL, BURN, COLGAN, SUTHERLAND] - Statement of intent about preferred options – including possible partnerships with Hugh Burn, |  |
| - Buildings and Heritage Features to be surveyed and Policy Proposed [AD] - List of Designated assets and Non- designated assets. - Non-designated heritage Assets – list to filter designated assets and non-designated that deserve policy intervention (from long list) - Map featuring heritage assets, housing and employment sites [AD] - Historic ‘core’ for Lowick? If so, where? [JH] - A Design Code for Lowick [from brief] |  |
| - Nature Conservation Policy to be expanded and revised [JD] - Nature conservation designations – statutory ones already protected – local nature reserves? |  |
| - Policy for Community Facilities to be written [KC] - Community Facilities – policy for them or not? Which ones? - Map to feature community facilities which need designating/protecting - Leisure facilities programme featuring green space on former football field, or South Road site to be explored with community representatives [tennis/bowls] |  |
| - The need for Policies on Housing, The Local Economy and Accessibility to be reviewed - Option for Development to be pursued with advice from CAN - Additional funding available for these – info to be provided |  |
| - Draft Statement or Vision to be drawn up for the Consultation Day [JH + JL + Group] |  |
| - A date for a local exhibition of the proposals for the plan to be arranged in June, after the meeting. | This I proposed for Saturday June 23rd |
| - Meeting to discuss feedback from the Exhibition: July 19th in the Village Hall | This is to be scheduled as part of Parish Council business, open to the Planning Group and others |
| - Plan to be written |  |

A meeting of the group will take place at 7.pm on May 9th at the Black Bull to discuss progress.